## Sheet1
Issue Type | Key | Summary | Status | Sprint | Assignee | Due date | Labels | Created | Updated | Reporter
Story | USPARK-17 | ReactJs with Vite for frontend | In Progress | USPARK Sprint 1 | Rathan | 2025-02-16 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-19 | Nodejs with Express for backend | To Do | USPARK Sprint 1 | koundinya pidaparthy | 2025-02-16 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-20 | MongoDb with Atlas for Database | In Progress | USPARK Sprint 1 | Rathan | 2025-02-16 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-21 | Aws Account Creation for Storing Medical Images | In Progress | USPARK Sprint 1 | AVINASH MANCHALA | 2025-02-16 |  | 2025-02-10 | 2025-02-17 | koundinya pidaparthy
Task | USPARK-22 | Data collection for AI ChatBot | To Do | USPARK Sprint 1 | Murali Kummari | 2025-02-15 |  | 2025-02-10 | 2025-02-15 | pranay kumar reddy
Story | USPARK-23 | Setup for testing using JestJs and Cypress | To Do | USPARK Sprint 1 | Sairam Maddela | 2025-02-16 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Task | USPARK-24 | Data collection for Image Analysis | To Do | USPARK Sprint 1 | pranay kumar reddy | 2025-02-15 |  | 2025-02-10 | 2025-02-15 | pranay kumar reddy
Story | USPARK-25 | Create a Readme file with basic steps to create setup in their local | To Do | USPARK Sprint 1 | Sujit Suprabhat Tubki | 2025-02-16 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Task | USPARK-26 | Processing the data for AI Chatbot | To Do | USPARK Sprint 1 | Murali Kummari | 2025-02-20 |  | 2025-02-10 | 2025-02-15 | pranay kumar reddy
Story | USPARK-27 | User OnBoarding Flow ( Register / Login using Clerk ) | To Do | USPARK Sprint 1 | Rathan | 2025-02-20 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Task | USPARK-28 | Processing the data for Image Analysis | To Do | USPARK Sprint 1 | pranay kumar reddy | 2025-02-20 |  | 2025-02-10 | 2025-02-15 | pranay kumar reddy
Task | USPARK-29 | Data collection for predictive analysis | To Do | USPARK Sprint 1 | L Uday Kumar Reddy | 2025-02-16 |  | 2025-02-10 | 2025-02-15 | pranay kumar reddy
Story | USPARK-30 | Doctor Registration and verification process | To Do | USPARK Sprint 1 | koundinya pidaparthy | 2025-02-20 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-31 | Admin Portal to control | To Do | USPARK Sprint 1 | AVINASH MANCHALA | 2025-02-20 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Task | USPARK-32 | Processing the data for predictive analysis | To Do | USPARK Sprint 1 | L Uday Kumar Reddy | 2025-02-20 |  | 2025-02-10 | 2025-02-15 | pranay kumar reddy
Story | USPARK-33 | Setting up State management using Redux. | To Do | USPARK Sprint 1 | koundinya pidaparthy | 2025-02-20 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-34 | Routes creation for backend and user validations | To Do | USPARK Sprint 1 | koundinya pidaparthy | 2025-02-20 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-35 | Creating Schemas for profiles | To Do | USPARK Sprint 1 | Rathan | 2025-02-20 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-36 | Creating test cases for login and registration screens using cypress | To Do | USPARK Sprint 1 | Sairam Maddela | 2025-02-26 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-37 | Prototype Design for AI Chatbot | To Do | USPARK Sprint 1 | Murali Kummari | 2025-02-27 |  | 2025-02-10 | 2025-02-15 | pranay kumar reddy
Story | USPARK-38 | Creating Documentation for Login and Registration Screens in React and Nodejs | To Do | USPARK Sprint 1 | Sujit Suprabhat Tubki | 2025-02-27 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-39 | Prototype Design for Image Analysis | To Do | USPARK Sprint 1 | pranay kumar reddy | 2025-02-27 |  | 2025-02-10 | 2025-02-15 | pranay kumar reddy
Story | USPARK-40 | Prototype Design for Predictive analysis | To Do | USPARK Sprint 1 | L Uday Kumar Reddy | 2025-02-27 |  | 2025-02-10 | 2025-02-15 | pranay kumar reddy
Story | USPARK-41 | Creating Landing Page and One Card Page | To Do | USPARK Sprint 1 | Rathan | 2025-03-06 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-42 | Create specific routes in backend - One card Questionaries | To Do | USPARK Sprint 1 | Rathan | 2025-03-07 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-43 | Create Valid schema in the backend | To Do | USPARK Sprint 1 | AVINASH MANCHALA | 2025-03-07 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-44 | Test the One Card Flow and landing page flow after login. | To Do | USPARK Sprint 1 | Sujit Suprabhat Tubki | 2025-03-07 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-45 | Document the Landing and One Card Pages and routes | To Do | USPARK Sprint 1 | Sujit Suprabhat Tubki | 2025-03-07 |  | 2025-02-10 | 2025-02-15 | koundinya pidaparthy
Story | USPARK-46 | API End point development | To Do | USPARK Sprint 1 | pranay kumar reddy | 2025-03-04 |  | 2025-02-10 | 2025-02-15 | pranay kumar reddy